## Sheet1
Task Timeline - End of Spring Semester 2023 (4/17/2023) | Start | End | Aaron | Ryan | Status
Document desired user pathways through the application | 2022-10-17 | 2022-10-24 | 50% - 2 hours | 50% - 2 hours | Complete
Contact actual venues/performers for opinions/experiences with booking | 2022-10-17 | 2022-10-31 | 75% - 3 hours | 25% - 1 hour | Complete
Document stack structure | 2022-10-17 | 2023-03-31 | 25% - 1 hour | 75% - 3 hours | Complete
Design and implement file structure | 2022-10-17 | 2022-10-31 | 50% - 4 hours | 50% - 4 hours | Complete
Develop and finalize mockups in Figma | 2022-10-24 | 2022-10-31 | 50% - 5 hours | 50% - 5 hours | Complete
Document thought process and inspiration behind page designs | 2022-10-24 | 2022-10-31 | 50% - 2 hours | 50% - 2 hours | Complete
Determine necessary properties associated to a band or venue (location, genre, capacity, etc.) | 2022-10-31 | 2022-11-07 | 25% - 1 hour | 75% - 3 hours | Complete
Construct flat files for each database element (account profiles, show info, pictures) | 2022-10-31 | 2022-11-07 | 75% - 3 hours | 25% - 1 hour | Complete
Populate flat files with test data | 2022-10-31 | 2022-11-07 | 50% - 2.5 hours | 50% - 2.5 hours | Complete
Implement JavaScript to the Figma Components (includes HTML and CSS) | 2022-12-05 | 2023-03-31 | 50% - 20 hours | 50% - 20 hours | Complete
Implement JavaScript for page funtionality | 2022-12-05 | 2023-03-31 | 50% - 16 hours | 50% - 16 hours | Complete
Implement 3rd party connections (Spotify, Apple Music, Maps, etc.) | 2022-12-05 | 2023-03-31 | 50% - 2 hours | 50% - 2 hours | Complete
|  |  | 61.5 hours | 61.5 hours